## nc_filtered
NC_ID | Model | Date | Component_No_or_Sl_No | Type_of_NC | Failure_Description | Test_Stage | Action_Plan_Advised | Action_Taken | Responsible_Person | Target_Closure_Date | Closure_Status | Closure_Date | Attachments | Created_At | Updated_At
NC-2025-0001 | 1110FM | 2025-10-14 | 1234 | Winding Resistance | UV= 3.81 & VW= 3.67 variation not ok | Testing | Rewinding or checking for damage |  | Rama | 2025-10-21 | Pending |  |  | 2025-10-14 13:56:12 | 2025-10-14 13:56:12
NC-2025-0002 | 1205D | 2025-10-14 | 1234 | Winding Resistance | Hv faila at 2.0 kv | Testing | Rebaking |  | Dhanush | 2025-10-17 | Pending |  |  | 2025-10-14 14:00:06 | 2025-10-14 14:00:06